
Stage
September 3-9 Stairwell closed for electricians. Coring and conduit install for antenna.
September 16-21 Roof work for steel install and roof repair for antenna placement
September 24-25 Install relocated antenna
July 28 - August 28 Lobby: Vertical pipe install, framing and drywall of chase, install of ornamental millwork around chase.
June 9 - August 10 Steam pipe install
September 16-21 Crane path
July 27 - October 2 Build single use bathrooms and hallway.






July 14 - November 20 Link Construction
July 9 - August 4 Chilled Water Line Install to Canning Center
August 5 - August 11 Sidewalk Install
HARPER COLLEGE CHILLED WATER & STEAM LINE PROJECT
Site Logistics Plan
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